## Slide 1: WFCAM Science Archive
Critical Design Review, April 2003
Management and Planning

## Slide 2: WFCAM Science Archive
Critical Design Review, April 2003
Context and Stakeholders
Project Definition
Management and Resources
Standards
Risk Assessment

## Slide 3: WFCAM Science Archive
Critical Design Review, April 2003
Context and Stakeholders
WSA is part of VDFS, funded through GSC as part of a PPARC Rolling Grant for the programme of Wide Field Astronomy and e-Science in the IfA
JAC and UKIDSS stakeholders requiring Science Archive for successful exploitation of WFCAM

## Slide 4: WFCAM Science Archive
Critical Design Review, April 2003
Project definition
Central rôle of Science Requirements Analysis
Science-driven
Developed and agreed with stakeholders
Avoid specification creep

## Slide 5: WFCAM Science Archive
Critical Design Review, April 2003
Project definition : a phased approach
Version 1 : available for WFCAM first light 2003/4
Version 2 : benefit from concurrent evaluation of
DBMS for large scientific archives
VISTA SA : to follow

## Slide 6: WFCAM Science Archive
Critical Design Review, April 2003
Key dates for the whole programme
WFCAM CDR Sep 2002
WSA SRAD agreed Dec 2002
WSA CDR Apr 2003
SSA (V1 prototype) Jun 2003
WSA V1 operable Jan 2004
WSA V2 CDR Apr 2004
WSA V2 operable Jan 2005
VISTA SA Phase B Feb 2005
VISTA SA operable Sep 2006

## Slide 7: WFCAM Science Archive
Critical Design Review, April 2003
WFCAM in use
VISTA in use
Whole Programme

## Slide 8: WFCAM Science Archive
Critical Design Review, April 2003
Project definition : Version 1
Analysis & Design phase - leading to CDR
V1 Build phase – 2003 April – November
V1 Integration & test phase – to December

## Slide 9: WFCAM Science Archive
Critical Design Review, April 2003
Version 1 Analysis & Design phase
Analysis of Science Requirements
Presentation of SRAD to UKIDSS November
Preliminary design: dataflow, DBMS schemas,
User Interface
Tests of disk access and data transfer speeds
Preparation of CDR documentation
completed April 2003

## Slide 10: WFCAM Science Archive
Critical Design Review, April 2003
WFCAM in use
VISTA in use
}
V1 Build phase
CDR

## Slide 11: WFCAM Science Archive
Critical Design Review, April 2003
Planning of Version 1 Build phase
Used SRAD + 20 “Usages of the WFCAM Science Archive”
and 20 “Curation Use cases” to identify work packages
(pieces of code, scripts) required
Effort required for each work package estimated
Work packages allocated to staff member(s)
Dependencies (internal and external) noted
Plan developed: Gantt chart and Quarterly work plans

## Slide 12: WFCAM Science Archive
Critical Design Review, April 2003
Version 1 Build phase (a) April - June
Build SSA = SuperCosmos Sky Archive (1.26 TB) in
SQL Server on WFCAM Science Archive Hardware
provide a working service to users and developers to
exercise prior to arrival of many TB of WFCAM data
Refine DB schemas and develop source ingest tools
Start image tools

## Slide 13: WFCAM Science Archive
Critical Design Review, April 2003
V1 Build phase – (a) April-June
SSA on-line

## Slide 14: WFCAM Science Archive
Critical Design Review, April 2003
Version 1 Build phase (b) July - November
continue development of ingest / Curation tools
continue development of User Access tools
acquire and install pixel hardware
use SSA as test-bed for Curation & User Access tools
in parallel, continue work on DBMS (Oracle, DB2) testing for Version 2

## Slide 15: WFCAM Science Archive
Critical Design Review, April 2003
V1 Build phase (b)

## Slide 16: WFCAM Science Archive
Critical Design Review, April 2003
Version1 Integration & Test : Nov - Dec
many components will have been tested using SSA
integrate pixel store access with DBMS
test remaining components and prepare for WFCAM data

## Slide 17: WFCAM Science Archive
Critical Design Review, April 2003
WFCAM in use
VISTA in use
Ingest commissioning data

## Slide 18: WFCAM Science Archive
Critical Design Review, April 2003
WSA Version 2 development
Study of scalability and DBMS concurrent with V1 work
As for V1, used SRAD + 20 “Usages of the WSA”
and 20 “Curation Use cases” to identify work packages
(pieces of code, scripts) required and effort estimated
These include migration to different RDBMS if required
(not a large component as hard work all been done!)
Detailed design to be prepared for reviewed in April 2004

## Slide 19: WFCAM Science Archive
Critical Design Review, April 2003
Management and Resources
Management reflects VDFS funding by GSC
VDFS : PI : Emerson + Management Team:
Lawrence (VDFS co-I) & McMahon (VDFS co-I),
Stewart (VPO), Irwin (CASU), Williams (WFAU)
Resources provided through WFAU rolling grant

## Slide 20: WFCAM Science Archive
Critical Design Review, April 2003
Managed as a part of VDFS

## Slide 21: WFCAM Science Archive
Critical Design Review, April 2003
WFAU staff working on Archive meet weekly to review progress and allocate tasks
Minutes of these meetings are provided to PI + Management Team and available to JAC
WFAU Manager reports progress against plans to PI + Management Team every month
Quarterly work plans and deliverables are scrutinised and plans revised as necessary
Report to Grid Steering Committee each ~ 6 months
Hierarchy of time-scales to track progress

## Slide 22: WFCAM Science Archive
Critical Design Review, April 2003
e.g. Q2 plan
cf. Gantt chart

## Slide 23: WFCAM Science Archive
Critical Design Review, April 2003
Archive staff share information using the WFAU Twiki collaborative WWW site
Formal and informal documents
Notes from external meetings and visits
Equipment set-ups and hardware experiments
(not public documentation so can be frank
about commercially sensitive material)
Public documentation is maintained on WFCAM Web pages

## Slide 24: WFCAM Science Archive
Critical Design Review, April 2003
Resources : Staff
1. Staff Effort (2.5 FTE) through WFAU grant for Archive:
Hambly (70%)
Bond (70%)
Read (50% to 100%)
Sutorius (50%)
MacGillivray (10%)
2. Other WFAU effort, which assists Archive work:
MacGillivray (20%, systems)
Sutorius (50%, systems)
Williams (50%, management)
3. Assistance and advice, especially DBMS, from Mann (WFAU, NeSC and AstroGrid), also NeSC, University, Oracle, IBM and Microsoft

## Slide 25: WFCAM Science Archive
Critical Design Review, April 2003
Resources : Equipment
Preliminary studies use equipment provided by University,
JREI awards, WFAU PPARC Rolling Grant
Disk access tests use equipment loaned by supplier
Equipment required for Archive discussed tomorrow

## Slide 26: WFCAM Science Archive
Critical Design Review, April 2003
Standards
Languages and libraries specified
Coding standards: follow ALMA (but CVS)
Use CVS (provided by UKATC)
Use javadoc and doxygen for source code

## Slide 27: WFCAM Science Archive
Critical Design Review, April 2003
Risk Assessment
Risk register will be maintained
Major internal / external risks identified
Likelihood, Effect and Impact (= L x E)
Mitigation considered

## Slide 28: WFCAM Science Archive
Critical Design Review, April 2003
Event | L | E | I | Mitigation
Serious illness or loss of staff | 1 | 3 | 3 | De-scope, delay lower priority items
Delay in delivery of V1 server | 2 | 2 | 4 | not on critical path 1 month
SSA implementation underestimated | 1 | 3 | 3 | Not on critical path 1 month
SQL Server not sufficiently scalable | 1 | 3 | 3 | Test by production of SSA prototype (1.26 TB)
DB Relational model failure | 1 | 3 | 3 | Submit plan to CDR, seek advice SDSS & DBMS contacts
Network too slow / expensive for data transfer | 1 | 3 | 3 | Use similar method as for JAC to CASU data transfer
CASU / external tools late | 1 | 2 | 2 | Use preliminary versions supplied

## Slide 29: WFCAM Science Archive
Critical Design Review, April 2003
Event | L | E | I | Mitigation
Catalogue data trawl rate too slow | 2 | 1 | 2 | Revise design for Version 2
Failure to agree JAC-CASU meta-data | 1 | 3 | 3 | Sort out through Management Team
Failure to make interfaces work | 1 | 3 | 3 | Seek specialist advice
Pixel processing tools fail | 1 | 3 | 3 | Seek local/external advice
Delay in delivery of pixel store hardware | 1 | 2 | 2 | Not on critical path for 1 month

## Slide 30: WFCAM Science Archive
Critical Design Review, April 2003
Summary
Planning and design follow an incremental approach, building on SSS, 6dF work to make best use of staff experience and mitigate risks
Management includes tracking progress on hierarchy of timescales and is integrated with that of the WFCAM pipeline through the VDFS Management Team